STAKEHOLDER REGISTER

TCC Expansion — IS Infrastructure Refresh

Draft v1.0 — March 27, 2026 — IS PMO Review Required

| Name | Role / Organization | Interest | Influence | Impact | Engagement | Engagement Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| Carri Sampson | TCC Manager / Project Sponsor — Metro Transit | High: operational continuity, operator welfare during displacement | High: approves scope, resources | High: operations depend on IS delivery | Lead | Primary sponsor. Weekly updates. SteerCo chair. Escalation point for all IS delivery issues. |
| Chad Ladda | TCC Assistant Manager — Metro Transit | High: daily TCC operations, Room 1007 readiness | High: day-to-day decisions | High | Manage closely | Primary daily contact. Coordinates IES/Solacom in Room 1007. Represented Carri at SteerCo Mar 25. |
| Gretchen White | IS Director / CIO — Metropolitan Council | Medium-High: IS resource allocation, budget | High: IS resource decisions | High: approved dedicated endpoint resource in principle | Keep satisfied | Monthly SteerCo. Escalation for resource decisions. Agreed endpoint resource — confirm who/when at Apr 22. |
| MayAnn Severud | IS PMO Manager — Metropolitan Council | Medium: IS PMO standards, artifact compliance | Medium: IS PMO oversight | Medium: audit sign-off required | Keep informed | PMO artifact review. IS PM's manager. Paul Burke also reports to her. |
| Robert Rimstad | MT Manager, Engineering & Construction | High: construction schedule, funding authorization | High: NTP authority, budget approval | High: all IS milestones depend on construction | Keep satisfied | Construction gate milestones. NTP timing. Transportation Committee liaison. Informed at SteerCo. |
| Mark Oelrich | Principal Project Coordinator — Metro Transit | High: construction schedule management | Medium: owns construction schedule | High: IS 1:1 slip rule applies | Keep informed | Weekly construction schedule updates. IS PM tracks via Monday brief. IS cannot influence — only monitor. |
| Paul Burke | IS Infrastructure PM / PMO — Met Council | High: IS infrastructure delivery across 3 projects | Medium-High: IS Network, Endpoint, Voice, Security | High | Manage closely | Direct weekly coordination. Objective-setting delivery model. Key resource for Room 1007 buildout. |
| Mark Linnell | IS Endpoint Manager — Met Council | Medium-High: PC procurement and deployment | Medium: endpoint delivery | High: EBC PC deployment is critical path | Manage closely | PC eval order submitted Mar 27. End-to-end deployment cycle to be mapped. New to role. |
| Eric Brown | LASO — Metropolitan Council | Medium: CJIS/BCA process | Medium: LASO authority on BCA submissions | High: BCA approval gates VuWall and Room 1007 | Manage closely | Assigned Mar 24. Engage immediately after Paul Burke meeting for Room 1007 firewall design. |
| Jacob Dada | Transit Applications Manager — Metro Transit | Medium: application deployment in PC cycle | Medium: handoff point in deployment chain | Medium | Keep informed | Part of PC deployment cycle. TransitMaster and specialized apps. Elevated permissions question TBD. |
| John Stefanko | Director IS Architecture — Met Council | Medium: IS architecture review | Medium: IS Triage team approval | Medium: triage review may be required for new infrastructure | Keep informed | IS Architecture (Triage) team lead. SteerCo attendee. NG911 and VuWall architecture review. |
| Lisa Belland | Business Continuity Manager — Met Council | High: COOP program alignment | Medium: COOP standards compliance | Medium: Room 1007 is a COOP facility | Keep informed | Room 1007 is a COOP facility. NG911 requirements workshop participant. COOP plan review. |
| Tracy French | IS Ops / CJIS SME — Met Council | Medium: CJIS compliance | Low-Medium: advisory role | Medium | Keep informed | Supports Eric Brown on CJIS scope. Consulted on BCA submissions. |
| Dale Tribbey | IS Voice Systems Engineer — Met Council | Medium: voice infrastructure delivery | Low-Medium: voice team execution | Medium | Keep informed | Voice system for Room 1007 and final space. Reports to Clete Erickson. |
| IES (Solacom Vendor) | External managed services vendor | Medium: EBC Room 1007 shared space, Solacom PCs | Low (TCC is primary interface) | Medium: firewall specs blocking power calculation | Monitor | Chad Ladda is primary IES interface. IS coordinates via Chad. IES firewall specs needed urgently. |

Engagement Levels: Lead = sponsor, active partner. Manage closely = frequent direct engagement required. Keep satisfied = periodic updates, escalate decisions. Keep informed = notify at milestones. Monitor = watch for changes.