COMMUNICATION PLAN

TCC Expansion — IS Infrastructure Refresh

Draft v1.0 — March 27, 2026 — IS PMO Review Required

| Communication | Audience | Frequency | Channel | Owner | Content | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Steering Committee Meeting | All SteerCo members (Carri, Chad, Gretchen, Robert Rimstad, John Stefanko, MayAnn, Josh Alswager, Antoinette Brasson) | Monthly — 3rd/4th Wednesday. Next: Apr 22, 2026 | Teams meeting + SharePoint site | PT (IS PM) | SteerCo deck + milestone status + RAID summary | Formal. Pre-read distributed 48 hrs prior. Action items logged in RAID. |
| IS PM Weekly Brief (Monday) | IS PM self / portfolio context | Weekly — Monday morning | Claude Desktop / personal PC | PT (IS PM) | Portfolio RAG, construction gate status, open actions, this week priorities | Internal IS PM planning tool. Outputs shared with team as needed. |
| Paul Burke Coordination | Paul Burke (IS Infra PM) | Weekly (or bi-weekly once cadence established) | Teams call or in-person | PT (IS PM) | IS infrastructure work package status, resource updates, change request tracking | Objective-setting model: IS PM hands off objective, receives cycle time, owner, ticket info. |
| TCC Day-to-Day Contact | Chad Ladda (TCC Asst Manager) | As needed — typically weekly | Teams chat / email | PT (IS PM) | EBC operational questions, IES coordination, Room 1007 updates | Primary daily TCC contact. Escalate to Carri Sampson for sponsor-level decisions. |
| IS PMO Status Report | MayAnn Severud, IS PMO | Per IS PMO cadence (to be confirmed) | SharePoint IS PMO List (MS Teams List) | PT (IS PM) | Weekly one-row RAG status per project — feeds IS PMO dashboard | Submit via IS Status Summary SharePoint List on TCCISPortfolioHub. |
| Construction Gate Monitoring | IS PM (monitor only) / Mark Oelrich (construction PM) | Weekly — construction schedule review | Email / Mark Oelrich updates | PT (IS PM) | NTP status, construction activity dates, any schedule changes | IS cannot influence construction. Monitor only. 1:1 slip rule applied to IS milestones. |
| Stakeholder Executive Update | Gretchen White, Robert Rimstad | At key milestones (M-03, M-05, M-08, M-09) | Email summary or brief deck | PT (IS PM) | Milestone achievement, risks, upcoming decisions | Concise, executive-facing. No technical detail. RAG status only. |
| CJIS/BCA Coordination | Eric Brown (LASO), Tracy French (CJIS SME) | As needed — key gates: Room 1007 design (Apr), BCA submission (Jun) | Email / Teams | PT (IS PM) + Paul Burke | Design documentation, BCA submission status, approval tracking | Engage Eric Brown immediately after Paul Burke meeting (Mar 30) with Room 1007 firewall design detail. |
| PC Deployment Coordination | Mark Linnell (Endpoint), Jacob Dada (Transit Apps) | Weekly during active deployment | ServiceWorks tickets + Teams | PT (IS PM) + Paul Burke | PC imaging status, deployment cycle tracking, issue resolution | ServiceWorks tickets track all IS-to-IS requests. IS PM receives updates directly. |
| IS Infrastructure Teams Channel | IS project team (Paul Burke, Mark Linnell, Eric Brown, Dale Tribbey, Tracy French) | As needed — real-time | MS Teams — IS Portfolio Hub channel | PT (IS PM) | Day-to-day coordination, quick questions, document sharing | Posted in Portfolio channel of TCC IS Portfolio Hub Teams team. |
| Operator Communications | TCC Operators (30 operators across consoles) | At key milestones: before displacement, during, at return | Carri Sampson / Chad Ladda communicate to operators (IS PM provides talking points) | Carri Sampson | Displacement timeline, what to expect, PC changeover instructions | IS PM provides content. TCC management communicates to operators. IS does not communicate directly to operators. |

# Communication Principles

- IS PM does not communicate directly to TCC operators — all operator-facing communication routes through Carri Sampson or Chad Ladda.

- Executive communications (Gretchen White, Robert Rimstad) are concise and RAG-status focused. No technical infrastructure detail in executive comms.

- SharePoint IS Portfolio Hub is the authoritative document repository. All project artifacts are stored there.

- ServiceWorks tickets are the formal mechanism for all IS-to-IS work requests. IS PM receives updates directly.

- Steering Committee is the formal decision authority for scope, resource, and milestone changes. Operational decisions are made at IS PM / IS Director level.

- Construction-related communications are IS PM monitoring only — IS does not communicate to the construction team directly. Route through Carri Sampson or Robert Rimstad.