## Slide 1
METROPOLITAN COUNCIL · METRO TRANSIT · INFORMATION SERVICES
TCC IS Projects
Steering Committee — Inaugural Meeting
March 25, 2026
TCC Expansion — IS Lead
VuWall / KVM — IS Coordination
NG911 Refresh — IS Coordination
Presented by
PT (Ptahmes Tat-Siaka)
IS Senior PM / PMO — Metropolitan Council
ATTENDEES
· Carri Sampson — TCC Manager / Sponsor
· Chad Ladda — TCC Assistant Manager
· Gretchen White — IS Director / CIO
· Robert Rimstad — MT Engineering & Construction
· MayAnn Severud — IS PMO Manager
· John Stefanko — IS Architecture Director
· Josh Alswager — IS Principal Specialist
· Antoinette Brasson
· PT — IS Senior PM (facilitating)
CONFIDENTIAL — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 2
AGENDA
Steering Committee Kick Off · March 25, 2026
01
Portfolio Overview
Three IS projects, IS PM role, why this SteerCo exists
5 min
02
TCC Expansion — IS Scope
EBC Room 1007 buildout, PC refresh, construction dependency
10 min
03
VuWall Video Wall
POC scope, non-refundable commitment, BCA path, IS support gap
8 min
04
Solacom NG911 Refresh
IS strategic goal: full managed service, cloud-only, 24/7 disengagement
7 min
05
Resource & Governance
Shared IS resources, conflict map, SteerCo cadence
5 min
06
Open Items & Decisions
PO confirmation, endpoint resource, SteerCo actions
10 min
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 3
PORTFOLIO OVERVIEW
Three concurrent IS projects supporting TCC
Amber
TCC Expansion
IS Lead
IS owns full delivery
60 IS PCs — 30 consoles (2 each)
EBC temp ops: 16 PCs in Room 1007
Construction-gated schedule
CJIS certification required
Red
VuWall Video Wall / KVM
IS Coordination
TCC leads vendor engagement
POC: 1 workstation, AV LAN
PO issued March 26 — non-refundable
BCA/CJIS approval required
IS support gap to be resolved
Amber
Solacom NG911 Refresh
IS Coordination
Federal Engineering leads RFP
Cloud-hosted managed solution only
IS goal: eliminate Mitel dependency
Josh Alswager as IS rep
Multi-year — FE schedule to 2027
⚠ Construction Dependency (all three projects):
NTP expected mid-late April 2026 · Construction Sep 2026 · 1:1 Slip Rule applies · IS cannot influence construction schedule
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 4
TCC EXPANSION — IS SCOPE
IS Lead · PC Refresh 30 Consoles · EBC Temporary Operations
IS DELIVERY SCOPE
Phase 1 — EBC Room 1007
16 IS PCs across 8 stations (7 in Rm 1007 + 1 existing EBC)
Network Infrastructure
~2 switches + IS firewall + UPS in Room 1007. Power specs needed NOW.
CJIS Certification
Eric Brown (LASO) assigned. BCA design proposal before occupancy.
Change Requests
CR-T01 (network), CR-T02 (PCs) required before any work begins.
PC Deployment Cycle
IS imaging → Jacob Dada apps → TCC tech → operator-ready (cycle time TBD)
Phase 2 — Final Space
60 IS PCs across 30 consoles. Post-NTP, post-construction.
KEY MILESTONES
M-01
PC Procurement GO/NO-GO
Complete
Jan 31
M-02
CJIS Scope Confirmed
Complete
Feb 7
M-03
Room 1007 Equipment Ready
In Progress
Mar 9
M-04
EBC PC Eval Units Ordered
In Progress
Mar 27
NTP
Construction NTP
Pending
Mid-Late Apr
M-05
EBC Operational (7 stations)
Working Target
Apr 30
M-08
Final Space Clean-Room Ready
Construction Gate
Oct 31
M-09
TCC Go-Live — 30 Consoles
Construction Gate
Dec 15
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 5
VUWALL VIDEO WALL / KVM
IS Coordination · POC committed · PO issued March 26, 2026
WHAT IS IS DOING
Scope
1 operator workstation POC. Dedicated AV LAN. Portable rack. Evaluate before 30-station full deployment.
CJIS/BCA
BCA design proposal required. IS Network produces network docs. Eric Brown (LASO) submits to BCA.
Network
AV LAN provisioning: VLAN, IGMP/multicast, QoS at Minneapolis TCC. Change request CR-V01 required.
Commissioning
IS on-site support 2 days. Aug–Sep 2026 target (after BCA approval ~Aug).
KEY RISKS
Non-refundable
PO issued Mar 26. POC cost is committed. Go/no-go decision must be based on documented criteria — not sunk cost.
IS Support Gap
IS endpoint and voice teams likely lack VuWall skill set. Formal assessment needed before deployment.
BCA Schedule
IS Network unavailable Apr–May. BCA submission June 2026. Approval ~Aug. Commissioning late Aug at earliest.
Bluum Contract
State contract renewal did not materialize Mar–Apr 2026. Parallel paths: Bluum, SHI, co-op purchasing.
TIMELINE
Mar 26
PO issued. Full technical engagement begins immediately.
May 2026
IS Network produces AV LAN design documentation for BCA.
Jun 2026
BCA design proposal submitted (Eric Brown / LASO).
Aug 2026
BCA approval expected (~8 weeks after submission).
Aug–Sep 2026
Network pre-check, commissioning (2 days).
Sep–Nov 2026
POC evaluation and go/no-go review.
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 6
SOLACOM NG911 REFRESH
IS Coordination · Cloud-hosted managed solution only · Federal Engineering leads RFP
IS Strategic Objective
Cloud-hosted, fully managed NG911 solution — new vendor owns 100% end-to-end incident response. IS has zero 24/7 obligation. IS is not a 24/7 operation. New vendor handles all carrier and vendor escalations via letters of agency. IS is completely disengaged from the 911 incident response chain.
WHY THIS MATTERS TO IS
Current Problem
POTS/DID lines connect IS-managed Mitel to IS-managed Solacom — placing IS in the 911 incident response chain with no value add. 4 dedicated Mitel lines.
IS Direction Confirmed
Cloud-hosted managed solution only. On-premise is off the table. FE (Federal Engineering) has been engaged.
RFP Workshop (Next Step)
Deep-dive RFP requirements workshop to be scheduled with FE. IS goal: Mitel disentanglement must be a SHALL requirement — not negotiable.
Timeline
Multi-year program. FE schedule extends to 2027. No 2026 completion pressure — but RFP workshop is the near-term gate.
KEY PARTICIPANTS
IS Primary Rep
Josh Alswager
IS Principal Specialist. Former IS Network Mgr, PSAP background. Council technical watchdog in FE process.
RFP Lead (Procurement)
Steven Kensinger
Principal Contract Administrator, Regional Administration. Leads formal RFP advertisement + contract. Not IS Procurement.
IS Architecture
John Stefanko
Director IS Architecture (Triage team). Architecture review of NG911 solution. Workshop participant.
Business Continuity
Lisa Belland
Business Continuity Manager. Oversees COOP program. NG911 must align with COOP standards.
FE Project Manager
Tommy Thompson
Federal Engineering PM. IS PM's primary FE contact. Rob Jackson + Eric Parry as FE SMEs.
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 7
OPEN ITEMS & DECISIONS
Steering Committee — Action Items and Decisions Required
DECISION
VuWall
PO path and timeline confirmed
Owner: Tina Folch
Due: Mar 26
RESOLVED
ACTION
TCC Expansion
Dedicated endpoint resource — confirm who and when (Gretchen White agreed in principle)
Owner: Gretchen White
Due: Apr 22 SteerCo
OPEN
ACTION
TCC Expansion
Apr 30 EBC target — formal review with dependency chain at next SteerCo
Owner: IS PM
Due: Apr 22 SteerCo
OPEN
ACTION
VuWall
IS resource for POC support — confirm assignment after Paul Burke meeting
Owner: IS PM + Paul Burke
Due: After Mar 30
OPEN
ACTION
TCC Expansion
Room 1007 power requirements to contractor — IS + IES both holding
Owner: Paul Burke + IES via Chad
Due: ASAP
URGENT
GOVERNANCE
All Projects
SteerCo cadence confirmed: monthly, third/fourth Wednesday. Next: April 22, 2026.
Owner: IS PM
Due: —
CONFIRMED
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit
March 25, 2026

## Slide 8
NEXT STEPS
This week and before April 22 SteerCo
This Week
IS PM submits IS-to-IS service request for 3 eval PCs (2 Council/special-build + 1 LENS)
Paul Burke meeting Mar 30 — IS Infrastructure scope: network, voice, BCA, UPS, power specs
FE NG911 weekly Mar 27 — confirm status, schedule deep-dive RFP workshop
Publish TCC IS Portfolio Hub SharePoint site — send link to all SteerCo attendees
April 2026
Confirm dedicated endpoint resource (Gretchen White — who and when)
Submit CR-T01 (Room 1007 network) as soon as power specs confirmed
Order Room 1007 gear: switches, firewall, UPS — do not wait for construction schedule
VuWall BCA design docs (IS Network produces, Eric Brown reviews)
April 22 SteerCo
Apr 30 EBC target — hard revised date with full dependency chain
VuWall BCA timeline acknowledgment (Jun/Jul, not May)
Dedicated endpoint resource — confirmed assignment or agreed alternative
Construction NTP update from Robert Rimstad — initiate IS final-space planning
INTERNAL USE ONLY — IS PMO · Metropolitan Council · Metro Transit · Next SteerCo: April 22, 2026
March 25, 2026