## README
TCC IS Portfolio Hub
WBS v3.2 — Draft Rows for Review
Prepared 2026-04-22 · Step 2 deliverable (v2 with dates)
Purpose
Row-level draft of 118 new tasks agreed in the red-line plan, with PlannedStart / PlannedEnd populated. Second red-line happens on THIS file - review row titles + dates, adjust, drop duplicates with existing v3.1 rows. Then rows flow to IS Project Tasks via Claude-in-Chrome SP REST.
Status coloring on v3.2 New Tasks
Green fill | Complete - back-dated retrospective work or recently-closed tasks; 100% PercentComplete, ActualEnd set.
Yellow fill | Active - in progress now; partial PercentComplete, RAGStatus Amber.
No fill (white) | Not Started - forward-dated; 0% PercentComplete, RAGStatus Not Started.
Date-source key in Notes
BACK-DATED | Historical event; suggested date is best-guess. PM to confirm.
PM-provided | Date given explicitly by PM (e.g., Chad eval Apr 27-May 7, OMF order end of May).
Inferred | Date derived from project memory + standard lead times. Flagged for PM adjustment.
PC Procurement restructure
PC Procurement expanded to 11 rows covering full 91-PC scope per PM: 18 OMF (14 operator station + 4 EBC Manager, ONE order) + 36 MTPD + 37 Council. Added: Funding String Analysis (Deliverable, now - refresh vs project funds), Demo Unit Evaluation (Apr 27-May 7 gate), and separate PO rows per audience. Schedule: eval Apr 27-May 7; OMF order May 8-31 immediately after eval; MTPD+Council orders May 15-Jun 15 (RAM price pressure); delivery Nov 2026; imaging Nov-Jan; testing Jan-Feb; sign-off Feb 28; go-live Mar 15 2027.
Room 1007 Temp Space pull-ahead
Target is now pre-State-Fair readiness per PM (late Aug). Setup & Build-Out: Jan-Jul 31 (Active, pulled from Apr 30). Go-Live / Operational: Aug 15 target (earlier if achievable). Keep pushing through the Apr 30 original target; this update reflects realistic slip.
Network & CJIS pull-ahead
Network Council/MTPD prep work pulled forward to Apr-Sep per PM - lab config + testing can proceed ahead of construction. Go-Live stays Construction Gate (install + cutover need TCC Final complete AND CJIS). CJIS Documentation pulled earlier: LASO Review Apr-May, BCA (if needed) Jun-Aug, Sign-Off Sep 15. CJIS thumbs-up is the critical gate for network install.
Funding string rules (per PM)
Refresh funds: existing equipment replacement + net new equipment. All 91 PCs are refresh-funded (18 OMF including the 4 EBC Manager + 36 MTPD + 37 Council). Project funds: monitors across the project. Funding String Analysis deliverable finalizes this BEFORE orders are placed.
Column mapping to SP
Title | SP Title. Format: 'Workstream · Task' with middle dot.
Project | SP Project choice: TCC Expansion / NG911 Refresh / VuWall.
TaskType | SP TaskType choice: Task / Milestone / Construction Gate / Deliverable.
Workstream | SP Workstream text column. Free text; grouping key.
PlannedStart / PlannedEnd / ActualEnd | SP DateTime. ActualEnd set only on Complete rows.
PercentComplete | SP Number. 100 Complete / partial Active / 0 Not Started.
RAGStatus | SP Choice: Complete / Amber / Not Started (Green and Red reserved for future use).
IsActive | SP Boolean. TRUE for all new rows.
Notes | SP Note. Date-source flag + rationale + cross-references.
What is NOT in this file
• No existing v3.1 rows (this file adds only). • No Phase / WBSNumber assignments - left blank; PM to assign at import or leave null. • No Owner / AssignedTo - left blank. • No Priority - left blank. • No dashboard / Power Fx changes - v32.10 refactor follows separately after import.

## v3.2 New Tasks
# | Title | Project | TaskType | Workstream | PlannedStart | PlannedEnd | ActualEnd | PercentComplete | RAGStatus | IsActive | Notes
1 | PC Procurement · Requirements & Change Ticket | TCC Expansion | Task | PC Procurement | 2026-03-01 | 2026-04-22 | 2026-04-22 | 100 | Complete | TRUE | Covers full PC scope: 18 OMF + 4 EBC Manager + 36 MTPD + 37 Council = 95 PCs total.
2 | PC Procurement · Implementation Plan | TCC Expansion | Deliverable | PC Procurement | 2026-03-15 | 2026-05-15 |  | 60 | Amber | TRUE | Imaging approach, desk assignments, handover plan. Active - being finalized.
3 | PC Procurement · Funding String Analysis | TCC Expansion | Deliverable | PC Procurement | 2026-04-15 | 2026-05-15 |  | 20 | Amber | TRUE | Nail down funding strings BEFORE orders placed. Rule per PM: refresh funds = existing replacement + net new equipment; project funds = monitors. Planning work happens now.
4 | PC Procurement · Demo Unit Evaluation | TCC Expansion | Task | PC Procurement | 2026-04-27 | 2026-05-07 |  | 0 | Not Started | TRUE | 10-day evaluation of demo units (2 Z2 + 1 CAD) starting Chad's return. Gates all four PC orders - once PC spec is locked, orders follow immediately.
5 | PC Procurement · OMF Bulk PC Order (18 units) | TCC Expansion | Task | PC Procurement | 2026-05-08 | 2026-05-31 |  | 0 | Not Started | TRUE | Immediate after eval complete per PM. 18 PCs total: 14 operator station PCs (7 consoles x 2) + 4 EBC Manager-Office PCs. Refresh-funded.
6 | PC Procurement · MTPD PC Order (36 units) | TCC Expansion | Task | PC Procurement | 2026-05-15 | 2026-06-15 |  | 0 | Not Started | TRUE | Shortly after OMF order (or combined) per PM - RAM price pressure drives urgency. 36 PCs for MTPD consoles; refresh-funded.
7 | PC Procurement · Council PC Order (37 units) | TCC Expansion | Task | PC Procurement | 2026-05-15 | 2026-06-15 |  | 0 | Not Started | TRUE | Parallel to MTPD. 37 PCs for Council consoles; refresh-funded.
8 | PC Procurement · Imaging & Build | TCC Expansion | Task | PC Procurement | 2026-11-01 | 2027-01-15 |  | 0 | Not Started | TRUE | PC delivery Nov 2026 per PM. Imaging starts on arrival; can overlap across orders.
9 | PC Procurement · Testing | TCC Expansion | Task | PC Procurement | 2027-01-01 | 2027-02-15 |  | 0 | Not Started | TRUE | Per-PC acceptance testing. PM adjust.
10 | PC Procurement · IS Acceptance / Sign-Off | TCC Expansion | Milestone | PC Procurement |  | 2027-02-28 |  | 0 | Not Started | TRUE | Inferred. PM adjust.
11 | PC Procurement · Go-Live | TCC Expansion | Milestone | PC Procurement |  | 2027-03-15 |  | 0 | Not Started | TRUE | Milestone TaskType (IS-owned date). PCs become production with construction + CJIS gates cleared.
12 | PC Deployment & Imaging · Requirements & Change Ticket | TCC Expansion | Task | PC Deployment & Imaging | 2026-04-01 | 2026-05-31 |  | 30 | Amber | TRUE | Monitor work rides this lane; no separate monitor workstream. Pulled earlier.
13 | PC Deployment & Imaging · Implementation Plan | TCC Expansion | Deliverable | PC Deployment & Imaging | 2026-05-01 | 2026-07-31 |  | 0 | Not Started | TRUE | Pulled earlier; can proceed in parallel with PC procurement. PM adjust.
14 | PC Deployment & Imaging · Monitor Procurement | TCC Expansion | Task | PC Deployment & Imaging | 2026-05-01 | 2026-07-31 |  | 0 | Not Started | TRUE | Monitors TBD per memory; project-funded. PM adjust.
15 | PC Deployment & Imaging · PC Deployment | TCC Expansion | Task | PC Deployment & Imaging | 2026-12-15 | 2027-02-15 |  | 0 | Not Started | TRUE | Starts as PC imaging wraps (Nov-Jan); Construction-gated for TCC Final. PM adjust once NTP lands.
16 | PC Deployment & Imaging · Monitor Deployment | TCC Expansion | Task | PC Deployment & Imaging | 2026-12-15 | 2027-02-15 |  | 0 | Not Started | TRUE | Parallel to PC Deployment.
17 | PC Deployment & Imaging · Testing | TCC Expansion | Task | PC Deployment & Imaging | 2027-02-15 | 2027-03-15 |  | 0 | Not Started | TRUE | Post-deployment in TCC Final. PM adjust.
18 | PC Deployment & Imaging · Back-out Plan (MPLS Monitor Migration) | TCC Expansion | Deliverable | PC Deployment & Imaging | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Mitigation: migrate MPLS monitors to OMF if monitor procurement slips. Sub-optimal; complicates fail-back.
19 | PC Deployment & Imaging · PC Sign-Off | TCC Expansion | Milestone | PC Deployment & Imaging |  | 2027-03-15 |  | 0 | Not Started | TRUE | Inferred.
20 | PC Deployment & Imaging · Monitor Sign-Off | TCC Expansion | Milestone | PC Deployment & Imaging |  | 2027-03-15 |  | 0 | Not Started | TRUE | Inferred.
21 | PC Deployment & Imaging · Go-Live | TCC Expansion | Construction Gate | PC Deployment & Imaging |  | 2027-03-31 |  | 0 | Not Started | TRUE | Construction Gate - TCC Final construction-dependent. Date inferred from Sep 2026 construction start + 4-6 mo duration.
22 | Network — Council · Requirements & Change Ticket | TCC Expansion | Task | Network — Council | 2026-04-01 | 2026-04-30 |  | 50 | Amber | TRUE | Pulled forward. Change ticket lead time is critical path.
23 | Network — Council · Implementation Plan | TCC Expansion | Deliverable | Network — Council | 2026-04-15 | 2026-05-31 |  | 0 | Not Started | TRUE | Pulled forward from Jul. Network prep can happen ahead of construction.
24 | Network — Council · Procurement / PO Tracking | TCC Expansion | Task | Network — Council | 2026-05-01 | 2026-06-30 |  | 0 | Not Started | TRUE | Switch / cable equipment; project-funded net new.
25 | Network — Council · 30-Console Capacity Analysis | TCC Expansion | Deliverable | Network — Council | 2026-04-15 | 2026-06-30 |  | 0 | Not Started | TRUE | Phase 2 pull-forward. Cross-references VuWall POC Design Phase 2 Infrastructure Location Analysis.
26 | Network — Council · Configuration / Build (Lab) | TCC Expansion | Task | Network — Council | 2026-06-01 | 2026-08-15 |  | 0 | Not Started | TRUE | Lab-configure equipment ahead of TCC Final. Per PM: could be ready April with CJIS thumbs-up; dates hold for CJIS LASO approval path.
27 | Network — Council · Testing (Lab) | TCC Expansion | Task | Network — Council | 2026-08-01 | 2026-09-30 |  | 0 | Not Started | TRUE | Bench testing before install. Decoupled from construction.
28 | Network — Council · Back-out Plan | TCC Expansion | Deliverable | Network — Council | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Pulled forward.
29 | Network — Council · Go-Live / Sign-Off | TCC Expansion | Construction Gate | Network — Council |  | 2026-12-15 |  | 0 | Not Started | TRUE | Construction Gate - install + cutover gated on TCC Final construction complete AND CJIS approval.
30 | Network — MTPD · Requirements & Change Ticket | TCC Expansion | Task | Network — MTPD | 2026-04-01 | 2026-04-30 |  | 50 | Amber | TRUE | Parallel change-ticket stream to Council. Pulled forward.
31 | Network — MTPD · Implementation Plan | TCC Expansion | Deliverable | Network — MTPD | 2026-04-15 | 2026-05-31 |  | 0 | Not Started | TRUE | Pulled forward.
32 | Network — MTPD · Procurement / PO Tracking | TCC Expansion | Task | Network — MTPD | 2026-05-01 | 2026-06-30 |  | 0 | Not Started | TRUE | Project-funded net new.
33 | Network — MTPD · 30-Console Capacity Analysis | TCC Expansion | Deliverable | Network — MTPD | 2026-04-15 | 2026-06-30 |  | 0 | Not Started | TRUE | Phase 2 pull-forward. Cross-references VuWall POC Design Phase 2 Infrastructure Location Analysis.
34 | Network — MTPD · Configuration / Build (Lab) | TCC Expansion | Task | Network — MTPD | 2026-06-01 | 2026-08-15 |  | 0 | Not Started | TRUE | Lab-configure ahead of TCC Final. CJIS approval gates install.
35 | Network — MTPD · Testing (Lab) | TCC Expansion | Task | Network — MTPD | 2026-08-01 | 2026-09-30 |  | 0 | Not Started | TRUE | Bench testing.
36 | Network — MTPD · Back-out Plan | TCC Expansion | Deliverable | Network — MTPD | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Pulled forward.
37 | Network — MTPD · Go-Live / Sign-Off | TCC Expansion | Construction Gate | Network — MTPD |  | 2026-12-15 |  | 0 | Not Started | TRUE | Construction Gate - install + cutover gated on construction AND CJIS.
38 | Voice / Solacom Crossover · Requirements & Change Ticket | TCC Expansion | Task | Voice / Solacom Crossover | 2026-07-01 | 2026-09-30 |  | 0 | Not Started | TRUE | On-hold during NG911 RFP - operating on existing Solacom; workstream holds coordination placeholder. Dates inferred to start post-vendor-selection.
39 | Voice / Solacom Crossover · Implementation Plan | TCC Expansion | Deliverable | Voice / Solacom Crossover | 2026-10-01 | 2026-11-30 |  | 0 | Not Started | TRUE | Inferred.
40 | Voice / Solacom Crossover · Configuration / Build | TCC Expansion | Task | Voice / Solacom Crossover | 2026-11-15 | 2026-12-31 |  | 0 | Not Started | TRUE | Inferred.
41 | Voice / Solacom Crossover · Testing | TCC Expansion | Task | Voice / Solacom Crossover | 2026-12-15 | 2027-01-31 |  | 0 | Not Started | TRUE | Inferred.
42 | Voice / Solacom Crossover · Go-Live / Sign-Off | TCC Expansion | Construction Gate | Voice / Solacom Crossover |  | 2027-01-31 |  | 0 | Not Started | TRUE | Construction Gate.
43 | CJIS Documentation · Requirements | TCC Expansion | Task | CJIS Documentation | 2026-03-01 | 2026-04-30 |  | 50 | Amber | TRUE | In progress. CJIS approval is the critical gate for network install and PC deployment per PM.
44 | CJIS Documentation · LASO Review | TCC Expansion | Deliverable | CJIS Documentation | 2026-04-15 | 2026-05-31 |  | 0 | Not Started | TRUE | Pulled forward (was May-Jul). Covers both (a) general CJIS posture and (b) EBC discretionary determination. LASO ruling feeds RAID Assumption re: BCA requirement. Critical path for network + PC deployment unblock.
45 | CJIS Documentation · BCA Submission (if needed) | TCC Expansion | Deliverable | CJIS Documentation | 2026-06-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Pulled forward. Conditional - only if LASO escalates EBC. 8-10 week BCA cycle.
46 | CJIS Documentation · Sign-Off | TCC Expansion | Milestone | CJIS Documentation |  | 2026-09-15 |  | 0 | Not Started | TRUE | Pulled from Nov. CJIS thumbs-up unblocks network go-live + PC deployment production use.
47 | OCM / Training · Requirements | TCC Expansion | Task | OCM / Training | 2026-06-01 | 2026-07-31 |  | 0 | Not Started | TRUE | Inferred - follows PC procurement + network readiness.
48 | OCM / Training · Training Plan | TCC Expansion | Deliverable | OCM / Training | 2026-08-01 | 2026-09-30 |  | 0 | Not Started | TRUE | Inferred.
49 | OCM / Training · Delivery | TCC Expansion | Task | OCM / Training | 2026-10-01 | 2026-12-31 |  | 0 | Not Started | TRUE | Inferred.
50 | OCM / Training · Sign-Off | TCC Expansion | Milestone | OCM / Training |  | 2027-01-15 |  | 0 | Not Started | TRUE | Inferred.
51 | Room 1007 Temp Space · Space Identification & Finalization | TCC Expansion | Task | Room 1007 Temp Space | 2025-10-01 | 2025-10-31 | 2025-10-31 | 100 | Complete | TRUE | BACK-DATED. Completed Q4 2025. PM to confirm exact dates.
52 | Room 1007 Temp Space · Network Design (Encrypted Tunnel) | TCC Expansion | Deliverable | Room 1007 Temp Space | 2025-11-01 | 2025-12-15 | 2025-12-15 | 100 | Complete | TRUE | BACK-DATED. Network design simplified after encrypted-tunnel approach removed firewall dependency. PM to confirm dates.
53 | Room 1007 Temp Space · LASO Ticket & Approvals | TCC Expansion | Task | Room 1007 Temp Space | 2025-12-01 | 2025-12-31 | 2025-12-31 | 100 | Complete | TRUE | BACK-DATED. PM to confirm dates.
54 | Room 1007 Temp Space · Setup & Build-Out | TCC Expansion | Task | Room 1007 Temp Space | 2026-01-01 | 2026-07-31 |  | 50 | Amber | TRUE | ACTIVE - in progress. Target pulled from Apr 30 to Jul 31 per PM; pre-State-Fair readiness. Earlier is better; push continues.
55 | Room 1007 Temp Space · Go-Live / Operational | TCC Expansion | Milestone | Room 1007 Temp Space |  | 2026-08-15 |  | 0 | Not Started | TRUE | Built out, tested, ready-to-go BEFORE MN State Fair (late Aug) per PM. Earlier if achievable.
56 | Room 1007 Temp Space · Decommission Plan | TCC Expansion | Deliverable | Room 1007 Temp Space | 2026-10-01 | 2026-11-30 |  | 0 | Not Started | TRUE | Forward. Triggered by TCC Final construction complete.
57 | Room 1007 Temp Space · Equipment Relocation | TCC Expansion | Task | Room 1007 Temp Space | 2027-01-01 | 2027-02-15 |  | 0 | Not Started | TRUE | Return equipment to MPLS. Inferred.
58 | Room 1007 Temp Space · IES Solacom Coordination | TCC Expansion | Task | Room 1007 Temp Space | 2026-12-01 | 2027-02-15 |  | 0 | Not Started | TRUE | Coordinate with IES on Solacom equipment removal timeline - ties to RAID Action re: IES coordination.
59 | Room 1007 Temp Space · Cleanup & Return to Rail | TCC Expansion | Task | Room 1007 Temp Space | 2027-02-15 | 2027-03-15 |  | 0 | Not Started | TRUE | Inferred.
60 | TCC Operational Readiness · Requirements & Change Ticket | TCC Expansion | Task | TCC Operational Readiness | 2026-04-17 | 2026-06-30 |  | 30 | Amber | TRUE | Quantify TCC support needs per Chad Ladda's 4/17 'TCC Current State & Upcoming Needs' doc. Replacement interface for Paul Burke (now off this work).
61 | TCC Operational Readiness · Implementation Plan | TCC Expansion | Deliverable | TCC Operational Readiness | 2026-07-01 | 2026-09-30 |  | 0 | Not Started | TRUE | Recommend solution (person / KB / hybrid). IS SME leads quantify -> recommend -> shepherd path.
62 | TCC Operational Readiness · Configuration / Build | TCC Expansion | Task | TCC Operational Readiness | 2026-09-01 | 2026-11-30 |  | 0 | Not Started | TRUE | Shepherd implementation across voice / network / security / endpoint teams.
63 | TCC Operational Readiness · Testing | TCC Expansion | Task | TCC Operational Readiness | 2026-12-01 | 2027-01-31 |  | 0 | Not Started | TRUE | Validate solution (person / KB / hybrid) works in practice.
64 | TCC Operational Readiness · IS Acceptance / Sign-Off | TCC Expansion | Milestone | TCC Operational Readiness |  | 2027-02-15 |  | 0 | Not Started | TRUE | Inferred.
65 | Pre-RFP Discovery · Solacom EOL Assessment | NG911 Refresh | Task | Pre-RFP Discovery | 2024-06-01 | 2024-08-31 | 2024-08-31 | 100 | Complete | TRUE | BACK-DATED. Captures re-baseline story: Solacom approaching EOL. PM to confirm dates.
66 | Pre-RFP Discovery · Solacom Upgrade Proposal & Response | NG911 Refresh | Task | Pre-RFP Discovery | 2024-09-01 | 2024-12-31 | 2024-12-31 | 100 | Complete | TRUE | BACK-DATED. Vendor response: replace the whole system. PM to confirm dates.
67 | Pre-RFP Discovery · FE Cloud RFP Recommendation | NG911 Refresh | Deliverable | Pre-RFP Discovery | 2025-01-01 | 2025-06-30 | 2025-06-30 | 100 | Complete | TRUE | BACK-DATED. FE recommended cloud-hosted RFP path. PM to confirm dates.
68 | Pre-RFP Discovery · Pivot Decision Record | NG911 Refresh | Milestone | Pre-RFP Discovery |  | 2025-07-15 | 2025-07-15 | 100 | Complete | TRUE | BACK-DATED. Decision to pivot to cloud RFP.
69 | RFP & Requirements · Requirements & Change Ticket | NG911 Refresh | Task | RFP & Requirements | 2026-03-01 | 2026-04-17 | 2026-04-17 | 100 | Complete | TRUE | Apr 17 workshop already happened - per v3.1 existing milestone. COMPLETE.
70 | RFP & Requirements · Implementation Plan (RFP Process) | NG911 Refresh | Deliverable | RFP & Requirements | 2026-04-01 | 2026-06-30 |  | 40 | Amber | TRUE | Active. FE-led; IS contributes requirements input.
71 | RFP & Requirements · IS Requirements Input to FE | NG911 Refresh | Task | RFP & Requirements | 2026-04-01 | 2026-05-31 |  | 60 | Amber | TRUE | Active.
72 | RFP & Requirements · Review & Validate RFP Package | NG911 Refresh | Task | RFP & Requirements | 2026-06-01 | 2026-07-31 |  | 0 | Not Started | TRUE | Testing equivalent for a documentation workstream.
73 | RFP & Requirements · IS Acceptance / Sign-Off | NG911 Refresh | Milestone | RFP & Requirements |  | 2026-08-15 |  | 0 | Not Started | TRUE | Possible overlap with existing v3.1 milestone 'FE Design Recommendation Review (Apr 17 Workshop)' - verify before import.
74 | Vendor Selection & Contract · Requirements & Change Ticket | NG911 Refresh | Task | Vendor Selection & Contract | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Inferred.
75 | Vendor Selection & Contract · Evaluation Plan | NG911 Refresh | Deliverable | Vendor Selection & Contract | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Vendor evaluation criteria and methodology.
76 | Vendor Selection & Contract · Vendor Evaluation | NG911 Refresh | Task | Vendor Selection & Contract | 2026-09-01 | 2026-11-30 |  | 0 | Not Started | TRUE | Inferred.
77 | Vendor Selection & Contract · LASO Review (CJIS Compliance) | NG911 Refresh | Deliverable | Vendor Selection & Contract | 2026-10-01 | 2026-11-30 |  | 0 | Not Started | TRUE | Ensures cloud vendor meets CJIS before contract signature. FE handles compliance evaluation within RFP; IS tracks the gate.
78 | Vendor Selection & Contract · Contract Award | NG911 Refresh | Milestone | Vendor Selection & Contract |  | 2026-12-15 |  | 0 | Not Started | TRUE | Possible overlap with existing v3.1 milestone 'Vendor Selection & Contract Award' - verify before import.
79 | Vendor Selection & Contract · IS Acceptance / Sign-Off | NG911 Refresh | Milestone | Vendor Selection & Contract |  | 2026-12-31 |  | 0 | Not Started | TRUE | Inferred.
80 | Cloud Configuration · Requirements & Change Ticket | NG911 Refresh | Task | Cloud Configuration | 2027-01-01 | 2027-02-28 |  | 0 | Not Started | TRUE | Inferred - post contract award.
81 | Cloud Configuration · Implementation Plan | NG911 Refresh | Deliverable | Cloud Configuration | 2027-02-01 | 2027-04-30 |  | 0 | Not Started | TRUE | Inferred.
82 | Cloud Configuration · Configuration / Build | NG911 Refresh | Task | Cloud Configuration | 2027-03-01 | 2027-06-30 |  | 0 | Not Started | TRUE | Inferred.
83 | Cloud Configuration · Testing | NG911 Refresh | Task | Cloud Configuration | 2027-06-01 | 2027-07-31 |  | 0 | Not Started | TRUE | Inferred.
84 | Cloud Configuration · Back-out Plan | NG911 Refresh | Deliverable | Cloud Configuration | 2027-05-01 | 2027-06-30 |  | 0 | Not Started | TRUE | Service-impact scenarios for cloud cutover.
85 | Cloud Configuration · IS Acceptance / Sign-Off | NG911 Refresh | Milestone | Cloud Configuration |  | 2027-08-15 |  | 0 | Not Started | TRUE | Inferred.
86 | Cutover · Requirements & Change Ticket | NG911 Refresh | Task | Cutover | 2027-06-01 | 2027-07-31 |  | 0 | Not Started | TRUE | Highest-risk NG911 workstream.
87 | Cutover · Implementation Plan | NG911 Refresh | Deliverable | Cutover | 2027-07-01 | 2027-08-31 |  | 0 | Not Started | TRUE | Inferred.
88 | Cutover · Configuration / Build (Pre-Cutover) | NG911 Refresh | Task | Cutover | 2027-08-01 | 2027-09-30 |  | 0 | Not Started | TRUE | Inferred.
89 | Cutover · Testing (Pre-Cutover Validation) | NG911 Refresh | Task | Cutover | 2027-08-15 | 2027-10-15 |  | 0 | Not Started | TRUE | Inferred.
90 | Cutover · Back-out Plan | NG911 Refresh | Deliverable | Cutover | 2027-08-01 | 2027-09-30 |  | 0 | Not Started | TRUE | Inferred.
91 | Cutover · IS Acceptance / Sign-Off | NG911 Refresh | Milestone | Cutover |  | 2027-10-31 |  | 0 | Not Started | TRUE | Inferred.
92 | Cutover · Go-Live | NG911 Refresh | Milestone | Cutover |  | 2027-11-15 |  | 0 | Not Started | TRUE | Go-Live TaskType = Milestone (not construction-dependent). Inferred date.
93 | Decommission (Mitel lines) · Requirements | NG911 Refresh | Task | Decommission (Mitel lines) | 2027-11-01 | 2027-12-15 |  | 0 | Not Started | TRUE | 4-line decommission post-cutover.
94 | Decommission (Mitel lines) · Decommission Plan | NG911 Refresh | Deliverable | Decommission (Mitel lines) | 2027-12-01 | 2027-12-31 |  | 0 | Not Started | TRUE | Inferred.
95 | Decommission (Mitel lines) · Execute (4 lines) | NG911 Refresh | Task | Decommission (Mitel lines) | 2028-01-01 | 2028-02-29 |  | 0 | Not Started | TRUE | Inferred.
96 | Decommission (Mitel lines) · Verify | NG911 Refresh | Milestone | Decommission (Mitel lines) |  | 2028-03-15 |  | 0 | Not Started | TRUE | Inferred.
97 | POC Design · Requirements & Change Ticket | VuWall | Task | POC Design | 2026-03-26 | 2026-04-30 |  | 60 | Amber | TRUE | PO issued Mar 26 per memory. Active.
98 | POC Design · Implementation Plan | VuWall | Deliverable | POC Design | 2026-04-15 | 2026-06-15 |  | 20 | Amber | TRUE | Active.
99 | POC Design · Phase 2 Infrastructure Location Analysis | VuWall | Deliverable | POC Design | 2026-05-01 | 2026-07-31 |  | 0 | Not Started | TRUE | MPLS data-room vs. data-center evaluation + chassis/blade needs at 30-console scale. Cross-references Network Council/MTPD 30-console capacity rows.
100 | POC Design · Configuration / Build (Spec) | VuWall | Task | POC Design | 2026-05-01 | 2026-07-31 |  | 0 | Not Started | TRUE | Inferred.
101 | POC Design · Testing (Spec Review) | VuWall | Task | POC Design | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Inferred.
102 | POC Design · IS Acceptance / Sign-Off | VuWall | Milestone | POC Design |  | 2026-09-15 |  | 0 | Not Started | TRUE | Inferred.
103 | POC Build · Requirements & Change Ticket | VuWall | Task | POC Build | 2026-07-01 | 2026-08-31 |  | 0 | Not Started | TRUE | Inferred.
104 | POC Build · Implementation Plan | VuWall | Deliverable | POC Build | 2026-08-01 | 2026-09-30 |  | 0 | Not Started | TRUE | Inferred.
105 | POC Build · Configuration / Build | VuWall | Task | POC Build | 2026-09-15 | 2026-11-15 |  | 0 | Not Started | TRUE | Inferred.
106 | POC Build · Testing | VuWall | Task | POC Build | 2026-10-15 | 2026-11-30 |  | 0 | Not Started | TRUE | Inferred.
107 | POC Build · Back-out Plan (Firewall / Switch-Port Rollback) | VuWall | Deliverable | POC Build | 2026-09-01 | 2026-10-15 |  | 0 | Not Started | TRUE | If POC gear has to come out.
108 | POC Build · IS Acceptance / Sign-Off | VuWall | Milestone | POC Build |  | 2026-12-15 |  | 0 | Not Started | TRUE | Inferred.
109 | POC Testing · Requirements & Change Ticket | VuWall | Task | POC Testing | 2026-11-01 | 2026-12-15 |  | 0 | Not Started | TRUE | Testing is the POC itself - evaluation criteria, results, IS acceptance.
110 | POC Testing · Evaluation Criteria & Test Plan | VuWall | Deliverable | POC Testing | 2026-11-01 | 2026-12-31 |  | 0 | Not Started | TRUE | Inferred.
111 | POC Testing · Execute Tests | VuWall | Task | POC Testing | 2026-12-15 | 2027-02-15 |  | 0 | Not Started | TRUE | Inferred.
112 | POC Testing · Results Analysis | VuWall | Task | POC Testing | 2027-02-01 | 2027-03-15 |  | 0 | Not Started | TRUE | Inferred.
113 | POC Testing · IS Acceptance / Sign-Off | VuWall | Milestone | POC Testing |  | 2027-03-31 |  | 0 | Not Started | TRUE | Inferred.
114 | BCA Submission · Requirements | VuWall | Task | BCA Submission | 2026-05-01 | 2026-06-15 |  | 0 | Not Started | TRUE | Inferred - target June submission per memory (conflicts with IS Network team unavailability Apr-May; starts May).
115 | BCA Submission · LASO Review | VuWall | Deliverable | BCA Submission | 2026-05-15 | 2026-06-30 |  | 0 | Not Started | TRUE | BCA intake path: design -> LASO -> BCA -> LASO thumbs-up -> deploy.
116 | BCA Submission · BCA Submission Package | VuWall | Deliverable | BCA Submission | 2026-06-15 | 2026-07-15 |  | 0 | Not Started | TRUE | Per memory: June target, falls back to Aug-Sep if missed.
117 | BCA Submission · Sign-Off (LASO Approval) | VuWall | Milestone | BCA Submission |  | 2026-09-30 |  | 0 | Not Started | TRUE | 8-10 week BCA cycle from July submission.
118 | Go/No-Go Decision · Decision Milestone | VuWall | Milestone | Go/No-Go Decision |  | 2027-04-15 |  | 0 | Not Started | TRUE | Single go/no-go decision point - after POC Testing complete. Inferred.
119 | Go/No-Go Decision · Deployment Plan | VuWall | Deliverable | Go/No-Go Decision | 2027-04-15 | 2027-06-30 |  | 0 | Not Started | TRUE | Inferred.
120 | Go/No-Go Decision · Disposition (Leave / Remove / Migrate) | VuWall | Milestone | Go/No-Go Decision |  | 2027-07-15 |  | 0 | Not Started | TRUE | POC equipment disposition at end of POC. Inferred.

## RAID Additions
# | RAID Type | Title | Project | Description | Status
1 | Assumption | BCA may be required for EBC scope | TCC Expansion | BCA may be required for EBC scope - LASO-discretionary until confirmed. Ties to CJIS Documentation LASO Review action. Close when LASO rules. | Open
2 | Opportunity | Phase 2 Network Capacity as its own forward workstream | TCC Expansion | Promote once VuWall current-state findings return. Ties to Network Council + MTPD 30-console Deliverable rows. | Open
3 | Action | Quantify TCC support needs (existing - stays open) | TCC Expansion | Per Chad Ladda's 4/17 'TCC Current State & Upcoming Needs' doc; IS SME leads. Parallel to TCC Operational Readiness workstream. Does NOT close until a dedicated resource solution is actually in place - naming the SME is a milestone within the action, not its resolution. | Open
4 | Action | IES coordination for Room 1007 decommission | TCC Expansion | Confirm IES Solacom equipment removal timeline alignment with IS equipment return to MPLS. Ties to Room 1007 decommission rows. | Open

## Row Count Summary
Row Count Summary
Project | Workstreams | Total Rows | Complete | Active | Not Started
TCC Expansion | 9 | 64 | 4 | 8 | 52
NG911 Refresh | 6 | 32 | 5 | 2 | 25
VuWall | 5 | 24 | 0 | 2 | 22
Total | 20 | 120 | 9 | 12 | 99
Per-workstream
Project | Workstream | Rows | Complete | Active | Not Started
TCC Expansion | PC Procurement | 11 | 1 | 2 | 8
TCC Expansion | PC Deployment & Imaging | 10 | 0 | 1 | 9
TCC Expansion | Network — Council | 8 | 0 | 1 | 7
TCC Expansion | Network — MTPD | 8 | 0 | 1 | 7
TCC Expansion | Voice / Solacom Crossover | 5 | 0 | 0 | 5
TCC Expansion | CJIS Documentation | 4 | 0 | 1 | 3
TCC Expansion | OCM / Training | 4 | 0 | 0 | 4
TCC Expansion | Room 1007 Temp Space | 9 | 3 | 1 | 5
TCC Expansion | TCC Operational Readiness | 5 | 0 | 1 | 4
NG911 Refresh | Pre-RFP Discovery | 4 | 4 | 0 | 0
NG911 Refresh | RFP & Requirements | 5 | 1 | 2 | 2
NG911 Refresh | Vendor Selection & Contract | 6 | 0 | 0 | 6
NG911 Refresh | Cloud Configuration | 6 | 0 | 0 | 6
NG911 Refresh | Cutover | 7 | 0 | 0 | 7
NG911 Refresh | Decommission (Mitel lines) | 4 | 0 | 0 | 4
VuWall | POC Design | 6 | 0 | 2 | 4
VuWall | POC Build | 6 | 0 | 0 | 6
VuWall | POC Testing | 5 | 0 | 0 | 5
VuWall | BCA Submission | 4 | 0 | 0 | 4
VuWall | Go/No-Go Decision | 3 | 0 | 0 | 3